## Estimate
OSI CoPilot - PD & Cloud Estimate
| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Basis
| Deloitte | Deloitte | Deloitte | non-DL | Deloitte | non-DL
AWS UNIT PRICES | Phase 1: Unit price; Phase 2: Unit
S3 Standard storage | Phase 1: 0.02116; Phase 2: EUR/GB/month
Avg page file size | Phase 1: 15; Phase 2: KB/page
Textract - DetectText (OCR) | Phase 1: 0.00138; Phase 2: EUR/page
Textract - Tables+Forms | Phase 1: 0.0598; Phase 2: EUR/page
Textract - Queries | Phase 1: 0.0138; Phase 2: EUR/page
% pages with tables/forms | Phase 1: 30%
% pages needing queries | Phase 1: 10%
LLM - extraction per CFR | Phase 1: 2.3; Phase 2: EUR/CFR
LLM - forbearance per CFR | Phase 1: 1.38; Phase 2: EUR/CFR
LLM - doc classifier per doc | Phase 1: 0.046; Phase 2: EUR/doc
LLM - embeddings per page | Phase 1: 9.2e-05; Phase 2: EUR/page
LLM - overhead factor | Phase 1: 15%
VOLUMES
# CFRs | 1 | 1 | 10 | 20 | 10 | 900 | Req: 300/mission, up to 900/bank
# Documents per CFR | 50 | 50 | 50 | 50 | 50 | 50 | 'each credit file contains on avg 50 documents'
# Pages per CFR (total across all docs) | 500 | 500 | 500 | 500 | 500 | 500 | 'each containing ~500 pages'. NOT per document.
Total documents | 50 | 50 | 500 | 1000 | 500 | 45000 | CFRs x docs/CFR
Total pages | 500 | 500 | 5000 | 10000 | 5000 | 450000 | CFRs x pages/CFR
PERSON-DAYS (build, one-time)
UC1: Corporate (BS, P&L, CF, Equity, DSCR, EBITDA) | 0 | 25 | 0 | 40 | 3 | 0 | Partly built. P2: add ratios.
UC1: Retail (DSTI, DTI, LTI, LTV, income) | 0 | 25 | 0 | 40 | 3 | 0 | Not built. New agent set.
UC1: Business plans, FX, trends | 0 | 12 | 0 | 30 | 2 | 0 | New doc types + cross-debtor views
UC2: Forbearance + IFRS9 staging | 0 | 18 | 0 | 20 | 3 | 0 | Built. P2: expand scope.
UC2: Reg. classification (NPE, POCI) | 0 | 15 | 0 | 25 | 3 | 0 | Not built. New dimension.
UC2: Other credit events + txn-level | 0 | 12 | 0 | 30 | 3 | 0 | Loan mods, insolvencies
Platform (dashboard, doc viewer, reports) | 0 | 15 | 0 | 25 | 3 | 0 | Severity rankings, source refs
Infra + CI/CD + multi-user | 0 | 15 | 0 | 30 | 4 | 0 | P2: basic. P4: enterprise SSO
P4: Architectural redesign | 0 | 0 | 0 | 100 | 0 | 0 | Batch, queues, rate limiting
P4: OSI Credit integration | 0 | 0 | 0 | 60 | 0 | 0 | Embed into ECB platform
P5: UAT | 0 | 0 | 0 | 0 | 40 | 0 | Test planning, execution, sign-off
TOTAL BUILD PD | 50K€ fixed | 137 | 0 | 400 | 64 | 0
PERSON-DAYS (ops, annual)
Prompt tuning + model updates | 0 | 0 | 5 | 0 | 0 | 12
Trigger / methodology updates | 0 | 0 | 3 | 0 | 0 | 8
User support + onboarding | 0 | 0 | 5 | 0 | 0 | 15
Testing + QA | 0 | 0 | 3 | 0 | 0 | 8
Infra, DevOps, security | 0 | 0 | 3 | 0 | 0 | 10
Documentation | 0 | 0 | 2 | 0 | 0 | 3
Monitoring, incidents, SLA | 0 | 0 | 0 | 0 | 0 | 12
TOTAL OPS PD / year | 0 | 0 | 21 | 0 | 0 | 68
CLOUD COSTS (annual euro)
Storage (S3 + vector DB + Postgres) | 5 | 10 | 180 | 330 | 180 | 950 | S3: pages x B8 KB / 1M x B7 $/GB/mo x 12 + DB + backups
Compute (ECS Fargate) | 0 | 600 | 3264 | 8664 | 2064 | 24480 | Backend + frontend + workers (P4/6) + ALB. Estimate.
Textract: OCR (all pages) | 1 | 1 | 7 | 14 | 7 | 621 | total pages x 0.0014 EUR/page
Textract: Tables+Forms (% of pages) | 9 | 9 | 90 | 179 | 90 | 8073 | total pages x 30% x 0.060 EUR/page
Textract: Queries (% of pages) | 1 | 1 | 7 | 14 | 7 | 621 | total pages x 10% x 0.014 EUR/page
LLM: Extraction agents | 2 | 2 | 23 | 46 | 23 | 2070 | CFRs x 2.30 EUR/CFR
LLM: Forbearance / classification | 1 | 1 | 14 | 28 | 14 | 1242 | CFRs x 1.38 EUR/CFR
LLM: Doc classifier | 2 | 2 | 23 | 46 | 23 | 2070 | total docs x 0.046 EUR/doc
LLM: Embeddings | 0 | 0 | 0 | 1 | 0 | 41 | total pages x 0.0001 EUR/page
LLM: Overhead (retries, testing) | 1 | 1 | 9 | 18 | 9 | 813 | 15% x LLM subtotal
TOTAL CLOUD / year | 22 | 627 | 3617 | 9340 | 2417 | 40981
SUMMARY
Build PD | 50K€ fixed | 137 | 0 | 400 | 64 | 0
Ops PD / year | 0 | 0 | 21 | 0 | 0 | 68
Cloud (annual) | 22 | 627 | 3617 | 9340 | 2417 | 40981
Cursor (Enterprise, licenses + tokens) | 0 | 4800 | 2400 | 0 | 2400 | 0 | Enterprise 200 EUR/user/mo. P2: 2 devs. P3,P5: 1 dev.
Phase 1 = 50K€ fixed (David). Phases 1-3,5 = Deloitte. Phases 4,6 = non-Deloitte.
500 pages per CFR total (across ~50 docs). NOT 500 per document.
Phase 4 includes architectural redesign - FORTUNA cannot scale to 300 CFRs as-is.
Phase 4 volume = 20 CFRs (dev/test only).
All unit prices in blue at top - change there, cloud costs recalculate.
LLM per-CFR costs based on FORTUNA benchmarks (7-10 EUR/run GPT-4o incl. retries).
PD rate not applied - Harshitha to set from rate card.